## Tabelle1
Hofer Levin & Wyss Julien BA Rough schedule |  | Geplant |  | Geplant Erledigt |  | Zu spät Erledigt
Topics | KW 9 | KW 10 | KW 11 | KW 12 | KW 13 | KW 14 | KW 15 | KW 16 | KW 17 | KW 18 | KW 19 | KW 20 | KW 21 | KW 22 | KW 23 | Meilensteine
Preparations
Hardware decision
Setting up Zephyr and the VM environment
Creation of basic framework of documentation & definition of topics
Setting up Git dev enviroment and testing Zephyr
Research on the NIST PQ standards
HW Sorting out the NIST PQ standards | [15 empty] | Recherche
Classification of NIST PQ standards
Research on comparable classical algorithms
HW Sorting comparable classical algorithms
Classification of comparable classical algorithms
Create a measurement scheme and test protocol
Implementation of Test Repo on Host
Implementation of multiple NIST PQ standards on HW
Implementation of several comparable classical algorithms
Testing and evaluation of the implemented NIST PQ standards on HW | [15 empty] | Implementation
Testing and evaluation of the implemented comparable classical algorithms | [15 empty] | & Testing
Comparison of NIST PQ standards and comparable classical algorithms
Evaluation of the comparison and conclusion
Write documentation
Report writing
Report Completion
Prepare BA defense | [15 empty] | Dokumentation
Create flyer (Aufgabenstellung)
Reserve
Final submission June 5